## Slide 1: TVET – Google Developer Training Cohort II

## Slide 2: TVET - Google Developer Training January- March 2023 Plan
Timeline | Milestone
5th Jan | Trainers Orientation
13th Jan | GoK ¦ MoE Briefing
16th Jan | HoDs Orientation
18th - 20th Jan | Tutors/Students Enrollment /Recruitment
21st – 22nd Jan | Deployment of Trainers to various institutions
23rd Jan | Tutor/Learners Orientation
23rd Jan - 3rd Feb | Onsite Training
24th Jan | Official Training kickoff
24th – 27th Jan | Unit 1: Introduction to Android Programming using Kotlin
30th Jan – 3 Feb | Unit 2: Setup Android Studio
6th – 10th Feb | Unit 3: Building Layouts
13th – 17th Feb | Unit 4: Writing Conditions in Kotlin

## Slide 3: TVET - Google Developer Training January 2023 Plan
Timeline | Milestone
17th – 24th Feb | Formation of GSDC
20th – 24th Feb | Unit 5: Working with Buttons
27th Feb – 3rd March | Unit 6: Interacting with UI and State
3rd March | Interim Report
6th – 10th March | Unit 7
13th – 17th March | Unit 8
20th – 24th March | Unit 9 and 10
27th – 31st March | Unit 11 & 12
3rd April | Final Report Submission

## Slide 4: Weekly Status Reports
Weekly project status reports shall be shared with the project leadership team every Friday of the week.
The weekly report shall include:
  Attendance status
  Course completion status
  GSDC formation status
  Assignment Status
  Badge earned